## Sprint1_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
Report - Introduction | Tùng | Document | 7 | 2021-10-31 | 2021-11-07 | 0
Report - Plan | Khuê | Document | 7 | 2021-10-31 | 2021-11-07 | 0
Class diagram - Basic | Trung | Document | 7 | 2021-10-31 | 2021-11-07 | 0
Database and Network research | All | Training | 7 | 2021-10-31 | 2021-11-07 | 0
Class diagram | All | Document | 3 | 2021-11-07 | 2021-11-10 | 0
Package diagram | All | Document | 3 | 2021-11-07 | 2021-11-10 | 0
Report - Analysis and Design | Khuê, Trung | Document | 4 | 2021-11-10 | 2021-11-14 | 0
Report - Implementation and Result | Tùng | Document | 4 | 2021-11-10 | 2021-11-14 | 0
Report redesignation | Tùng | Document | 1 | 2021-11-13 | 2021-11-14 | 0

## Sprint2_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
Database design | Khuê, Trung, Tùng | Database | 3 | 2021-11-14 | 2021-11-17 | 0
Data sample generation | Khuê, Tùng | Databse | 4 | 2021-11-17 | 2021-11-21 | 0
Report#2 drafting | Trung | Document | 4 | 2021-11-17 | 2021-11-21 | 0
Report#2 redesign | Tùng | Document | 1 | 2021-11-21 | 2021-11-22 | 0
Patient System - Server implementation | Khuê, Trung | Server | 7 | 2021-11-21 | 2021-11-28 | 0
Demo GUI implementation | Tùng | GUI | 6 | 2021-11-22 | 2021-11-28 | 0

## Sprint3_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
GUI design | Khuê, Trung, Tùng | Document | 3 | 2021-11-28 | 2021-12-01 | 0
Report#3 drafting and redesign | Tùng | Document | 4 | 2021-12-01 | 2021-12-05 | 0
Patient System - Server implementation (cont.) | Khuê, Trung, Tùng | Server | 4 | 2021-12-01 | 2021-12-05 | 0
Patient System - GUI implementation | Tùng | GUI | 7 | 2021-12-05 | 2021-12-12 | 0
Payment System - Server implementation | Khuê, Trung, Tùng | Server | 7 | 2021-12-05 | 2021-12-12 | 0

## Sprint4_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
Payment System - GUI implementation | Tùng | GUI | 7 | 2021-12-12 | 2021-12-19 | 0
Network connection implementation | Khuê, Trung | Network | 7 | 2021-12-12 | 2021-12-19 | 0
System Debug and Testing | Khuê, Trung | Testing | 4 | 2021-12-19 | 2021-12-23 | 0
Documents preparation | Tùng | Document | 4 | 2021-12-19 | 2021-12-23 | 0
Meeting preparation | Khuê, Trung, Tùng | Other | 3 | 2021-12-23 | 2021-12-26 | 0