## Sprint1_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
Report - Introduction | Tùng | Document | 7 | 2021-10-31 | 2021-11-07 | 0
Report - Plan | Khuê | Document | 7 | 2021-10-31 | 2021-11-07 | 0
Class diagram - Basic | Trung | Document | 7 | 2021-10-31 | 2021-11-07 | 0
Database and Network research | All | Training | 7 | 2021-10-31 | 2021-11-07 | 0
Class diagram | All | Document | 3 | 2021-11-07 | 2021-11-10 | 0
Package diagram | All | Document | 3 | 2021-11-07 | 2021-11-10 | 0
Report - Analysis and Design | Khuê, Trung | Document | 4 | 2021-11-10 | 2021-11-14 | 0
Report - Implementation and Result | Tùng | Document | 4 | 2021-11-10 | 2021-11-14 | 0
Report redesignation | Tùng | Document | 1 | 2021-11-13 | 2021-11-14 | 0

## Sprint2_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
Implementation - Patient System - Admin side | Trung | Coding | 14 | 2021-11-14 | 2021-11-28 | 0
Implementation - Patient System - Manager side | Khuê, Trung | Coding | 14 | 2021-11-14 | 2021-11-28 | 0
Implementation - Patient System - Patient side | Tùng | Coding | 14 | 2021-11-14 | 2021-11-28 | 0
Report update and redesignation | Tùng | Document | 3 | 2021-11-25 | 2021-11-28 | 0

## Sprint3_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
Implementation - Payment System - Manager side | Trung | Coding | 14 | 2021-11-28 | 2021-12-12 | 0
Implementation - Payment System - Patient side | Tùng | Coding | 14 | 2021-11-28 | 2021-12-12 | 0
System Synchronization | Khuê | Coding | 14 | 2021-11-28 | 2021-12-12 | 0
Report update and redesignation | Tùng | Document | 3 | 2021-12-09 | 2021-12-12 | 0

## Sprint4_Task
Task | Member | Type of Task | Duration | Start date | End date | Overdue
Implementation - Data Transfer via Network | All | Coding | 7 | 2021-12-12 | 2021-12-19 | 0
Component Testing | All | Coding | 2 | 2021-12-19 | 2021-12-21 | 0
System Testing | All | Coding | 3 | 2021-12-21 | 2021-12-24 | 0
Report update and redesignation | Tùng | Document | 3 | 2021-12-23 | 2021-12-26 | 0
Meeting preparation | All | Document | 2 | 2021-12-24 | 2021-12-26 | 0